GENERAL PROJECT INFORMATION

Project Information; Client Information. Project Name:; Riverside Fire Station No. 3 Renovation; Company Name:; Town of Riverside. Project Contact:; Jane Smith, PE; Client Contact:; Bob Johnson, Director of Public Works. Location:; 123 Main Street, Riverside, NY 11001; Address:; 456 Town Hall Road, Riverside, NY 11001. Phone:; (631) 756-8000; Phone:; (631) 555-0100. Fax:; (631) 756-8010; Fax:; (631) 555-0101. E-Mail:; jsmith@h2m.com; E-Mail:; bjohnson@riverside.gov.

PROJECT TEAM

The internal and external team members for this project include:

Name; Organization; Role; Email; Phone. Jane Smith; H2M; Project Manager; jsmith@h2m.com; (631) 756-8000. Tom Lee; H2M; Lead Architect; tlee@h2m.com; (631) 756-8001. Sara Chen; H2M; Civil Engineer; schen@h2m.com; (631) 756-8002. Bob Johnson; Town of Riverside; Client PM; bjohnson@riverside.gov; (631) 555-0100.

OVERVIEW

- Statement of Purpose

To provide the Town of Riverside with Design Development through Construction Administration phase services for the renovation of Fire Station No. 3, including a full interior renovation, ADA upgrades, MEP systems replacement, and exterior envelope improvements.

- Success Factors

Client's Critical Success Factors; Performance Objectives. 1; Manage construction costs; Metric:; Keep change orders under 5%. 2; On time delivery; Metric:; Construction start - March 2027. 3; Quality design; Metric:; Minimal RFIs and change orders. 4; Metric:. 5; Metric:.

H2M's Critical Success Factors; Performance Objectives. 1; Meets financial goals; Metric:; Achieve at least a 3.1 direct labor multiplier. 2; Adhere to project schedule; Metric:; Meet or exceed scheduled milestones. 3; Manage construction costs; Metric:; Keep change orders under 2%. 4; Metric:. 5; Metric:.

HEALTH & SAFETY

- Project Hazard Assessment

Site work occurs at an active fire station. Hazards include live apparatus bays, existing overhead utilities, and potential asbestos in the 1968 structure. Pre-construction survey and coordination with the Fire Chief required before mobilization.

PROJECT DELIVERABLES

- Meetings

Type; Frequency; Anticipated Attendees (By Title). Client kick-off; SD; CM, PM. Internal Design Progress Meetings; Bi-Weekly; CM, PM - Design Team. Construction progress; Bi-Weekly; CM, PM.

Drawings

Discipline; Dwg. #; # Dwg. Title. Architectural; A-101; # First Floor Plan.

Specifications

Div. - Section No.; # Specifications Section Name. 03 - 3000; # Cast-in-Place Concrete.

Cost Opinions

Milestone; Type / Title; # Link / Comments. D.D. Phase; Preliminary Cost Opinion; # By CM. C.D. Phase; Final Cost Opinion; By CM.

Reports

Milestone; Type / Title; # Link / Comments. Monthly; Progress Report; # Emailed to client.

WORK BREAKDOWN STRUCTURE (WBS)

- https://h2m.sharepoint.com/projects/RIVR-0031/WBS.xlsx

SCOPE OF WORK AND SERVICES

- Scope of Work

H2M will provide full architectural and engineering services for the renovation of Fire Station No. 3, including design development through construction administration.

- Scope of Services

Services include Schematic Design, Design Development, Construction Documents, Bidding and Procurement Assistance, and Construction Administration. H2M will coordinate all disciplines internally and manage all regulatory submissions.

PROJECT FINANCIALS

- https://h2m.sharepoint.com/projects/RIVR-0031/Project-Setup-Form.xlsx

Accounting Practices

Invoice Frequency & Send by Date Issue Invoice by. Frequency:; Monthly; Date:; 15th of each month.

SCHEDULE & MILESTONES

  - Detailed Project Schedule (Attach link)

- https://h2m.sharepoint.com/projects/RIVR-0031/Schedule.mpp

  - Project Milestones (Client Reviews, Regulatory submissions, etc.)

MILESTONES. No.; Milestone Description; Date. 1; Internal Design Team Kick-off Meeting; 2026-08-01. 2; External Client Kick-off Meeting; 2026-08-08. 3; Submit DD for QA Review; 2026-10-15. 4; Issue Bid Documents; 2027-01-15. 5; Bid Opening; 2027-02-05. 6; Construction Kick-off; 2027-03-01. 7; Substantial Completion; 2027-12-31.

Progress Reports

Frequency / Format / Delivery Method Format Delivery. Frequency:; Monthly; Format:; PDF; Delivery Method:; Email.

BIM/CAD REQUIREMENTS

- Attach link to separate BIM Execution Plan

- https://h2m.sharepoint.com/projects/RIVR-0031/BIM-Execution-Plan.docx

QA AND QC PLANS

- QA led by the Department Manager with formal reviews at DD and CD milestones. QC performed by discipline leads prior to each submission.

RISK MANAGEMENT PLAN

- Identify Project Risk Factors, Potential Impacts and Mitigation measures.

Risk Factors; Potential Impacts to CFSs; Severity (1 to 10); Probability (%); Priority Rating; Mitigation Measures; By Whom; By When. Staff availability across disciplines may delay design; Assumptions made, loss of efficiency and potential rework; 7; 40%; 2.8; Monitor progress; look for support opportunities; JBL; 2026-09-01. Construction cost may exceed available funds; Redesign required, impacting schedule; 8; 50%; 4.0; Cost opinion at each phase gate; CM; Each Phase. CFS – Critical Success Factor