GENERAL PROJECT INFORMATION

Project Information; Client Information. Project Name:; Click or tap here to enter text.; Company Name:; Click or tap here to enter text.. Project Contact:; Click or tap here to enter text.; Client Contact:; Click or tap here to enter text.. Location:; Click or tap here to enter text.; Address:; Click or tap here to enter text.. Phone:; Click or tap here to enter text.; Phone:; Click or tap here to enter text.. Fax:; Click or tap here to enter text.; Fax:; Click or tap here to enter text.. E-Mail:; Click or tap here to enter text.; E-Mail:; Click or tap here to enter text..

PROJECT TEAM

The internal and external team members for this project include:

Name; Organization; Role; Email; Phone. John Doe; H2M; … @ h2m.com; … @ h2m.com.

OVERVIEW

- Statement of Purpose

EXAMPLE: To provide the client with Design Development though CA phase services for the design and construction of a new two story, 3-bay fire station with approx.:

- 8,400 s.f. of first floor space

- 4,500 s.f. of second floor space

- 230 s.f. of mezzanine and

- 3,000 s.f. of occupiable roof terrace.

- 3,000 s.f. of basement space as an alternate

Architectural Schematic Design documents have been previously completed by H2M.

- Success Factors

Client's Critical Success Factors; Performance Objectives. 1; Manage construction costs; Metric:; Keep change orders under 5%. 2; On time delivery; Metric:; Construction start - Early March 2025. 3; Quality design; Metric:; H2Ms Quality Process documented, Minimal RFI, &l C.O.s. 4; Metric:. 5; Metric:.

H2M's Critical Success Factors; Performance Objectives. 1; Meets financial goals; Metric:; Achieve at least a 3.1 direct labor multiplier. 2; Adhere to project schedule; Metric:; Meet of exceed scheduled milestones. 3; Manage construction costs; Metric:; Keep change orders under 2%. 4; Metric:. 5; Metric:.

PROJECT DELIVERABLES

- Meetings

Type; Frequency; Anticipated Attendees (By Title). Client kick-off; SD; CM, PM. Internal Design Team Kick-off Meeting; Once; CM, PM - Design Team. Internal Design Progress Meetings; Bi-Weekly; CM, PM - Design Team. External Client Kick-off Meeting; Once; CM, PM - Design Team as deemed appropriate. External Client Touchbase; Bi-Weekly; CM, PM - Design Team as deemed appropriate. Pre-bid walk-through; Once; CM, PM. Bid opening; Once; CM, PM. Construction kick-off; Once; CM, PM. Construction progress; Bi-Weekly; CM, PM.

Drawings

Discipline; Dwg. #; # Dwg. Title. # Refer to Master Drawing List via this link.

Specifications

Div. - Section No.; # Specifications Section Name. # Refer to Master Drawing List via this link.

Cost Opinions

Milestone; Type / Title; # Link / Comments. D.D. Phase; Preliminary Cost Opinion; # By CM. C.D. Phase; Final Cost Opinion; By CM.

Reports

Milestone; Type / Title; # Link / Comments. D.D. Phase; Preliminary Cost Opinion; # By CM. C.D. Phase; Final Cost Opinion; By CM.

WORK BREAKDOWN STRUCTURE (WBS)

- Task Description, Schedule, and Budget
<Insert link to the detailed WBS developed for the project>

SCOPE OF WORK AND SERVICES

- Scope of Work

H2M will provide full architectural and engineering services for the renovation of Fire Station No. 3, including design development through construction administration. The project includes a full interior renovation, ADA upgrades, MEP systems replacement, and exterior envelope improvements.

- Scope of Services

<Describe in detail, the services that H2M will be providing in support of the above>

PROJECT FINANCIALS

- Fee and Task Breakdown [Phase, Discipline, Deliverable, Task(s)]
<Insert link to Project Set-up Form>

Accounting Practices

Invoice Frequency & Send by Date Issue Invoice by. Frequency:; Monthly; Date:.

SCHEDULE & MILESTONES

  - Detailed Project Schedule (Attach link)

- <Insert link to the detailed WBS developed for the project>

  - Project Milestones (Client Reviews, Regulatory submissions, etc.)

MILESTONES. No.; Milestone Description; Date. 1; Internal Design Team Kick-off Meeting; 2024-06-11. 2; External Client Kick-off Meeting; 2024-06-17. 3; Submit DD for QA Review; 2024-08-13. 4; DD Set to Owner & Estimator; 2024-08-26. 5; Estimate Due; 2024-09-18. 6; Internal Estimate Review; 2024-09-19. 7; External DD Estimate Review / CD Phase Kick-off w/ Client; 2024-09-23. 8; Submit CD for QA Review; 2024-12-03. 9; Print BID / CD Set; 2024-12-13. 10; Issue Bid Documents; 2025-01-06. 11; Pre-Bid Walk Through; TBD. 12; Bid Opening; 2025-01-24. 13; Notice of Award; 2025-01-29. 14; Negotiations & Contracts Complete; 2025-02-21. 15; Construction Kick-off; 2026-03-03. 16; Substantial Completion; 2026-05-31.

Progress Reports

Frequency / Format / Delivery Method Format Delivery. Frequency:; PDF; Format:; PDF; Delivery Method:; Email.

BIM/CAD REQUIREMENTS

- Attach link to separate BIM Execution Plan

- <Insert link to the detailed WBS developed for the project>

QA AND QC PLANS

- Identify key management participants and schedules for both QA and QC

RISK MANAGEMENT PLAN

- Identify Project Risk Factors, Potential Impacts and Mitigation measures.

Risk Factors; Potential Impacts to CFSs; Severity (1 to 10); Probability (%); Priority Rating; Mitigation Measures; By Whom; By When. There may be a delays for certain portions of the deign work due to staff availability in certain disciplines.; Project team will have to make assumptions resulting in loss of efficiency & potential rework.; 7; 40%; 2.8; Monitor progress, look for support opportunities to enable discipline to meet schedule; JBL; 2024-07-01. Construction cost may come in above client's available funds; Project will have to be redesigned to come in under client's available funds impacting schedule.; 8; "50%; 4.0; Each Phase. 0.0. 0.0. 0.0. 0.0. CFS – Critical Success Factor